## 1. Senior Design OP
Senior Design Operating Procedure
Activities |  |  | September | [26 empty] | October | [30 empty] | November | [29 empty] | December
|  |  | Week 1 |  |  |  |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17
|  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
|  |  | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun | Mo | Tu | We | Th | Fr | Sat | Sun
MEETINGS |  | Client Meetings (Friday 2pm-2:30pm) | bar: Week 5 4 Fr; Week 6 11 Fr; Week 7 18 Fr; Week 8 25 Fr; Week 9 1 Fr; Week 10 8 Fr; Week 11 15 Fr; Week 12 22 Fr; Week 13 29 Fr; Week 14 6 Fr; Week 15 13 Fr; Week 16 20 Fr
Team Meetings | bar: Week 5 1 Tu; Week 5 3 Th; Week 6 8 Tu; Week 6 10 Th; Week 7 15 Tu; Week 7 17 Th; Week 8 22 Tu; Week 8 24 Th; Week 9 29 Tu; Week 9 31 Th; Week 10 5 Tu; Week 10 7 Th; Week 11 12 Tu; Week 11 14 Th; Week 12 19 Tu; Week 12 21 Th; Week 13 26 Tu; Week 13 28 Th; Week 14 3 Tu; Week 14 5 Th; Week 15 10 Tu; Week 15 12 Th; Week 16 17 Tu; Week 16 19 Th
Senior Design (I) - CIS4951 | DEADLINES | Client Presentations and Course Overview (Sep 4) | bar: Week 1 4 We
Project Teams Formed, Client Presentations Summary (Sep 18) | bar: Week 3 18 We
Use Case Presentations (Oct 9) | bar: Week 6 9 We
Project Management Plan Presentations (Oct 23) | bar: Week 8 23 We
Specification Document Presentations (Nov 13) | bar: Week 11 13 We
SQA Plan Presentations (Dec 11) | bar: Week 15 11 We
| CHECK-IN | Project Teams Check-In #1 (Oct 1) | bar: Week 5 1 Tu
Project Teams Check-In #2 (Oct 15) | bar: Week 7 15 Tu
Project Teams Check-In #3 (Oct 29) | bar: Week 9 29 Tu
Project Teams Check-In #4 (Nov 13) | bar: Week 11 13 We
Project Teams Check-In #5 (Dec 4) | bar: Week 14 4 We
| FINAL | Postmortem and Feasibility Prototype Demo (11:30 to 2:30 PM) (Dec 18) | bar: Week 16 18 We

## 2. Project OP
Project Operating Procedure (OP)
Project | Tasks |  | Plan vs. Actual | 2024-01-01 | [12 empty] | 2024-02-01 | [20 empty] | 2024-03-24 | [20 empty] | 2024-04-24 | [21 empty] | 2024-05-01 | [22 empty] | 2024-06-01
|  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 2 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22
|  |  |  | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14
|  |  |  | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr
Project #1 Title: Goal: | Milestones |  |  | Week 1 16 Tu: ▼ Project kickoff; Week 4 8 Th: ▼ Checkpoint #1; Week 8 7 Th: ▼ Checkpoint #2; Week 12 4 Th: ▼ Checkpoint #3; Week 16 2 Th: ▼ Checkpoint #4; Week 20 30 Th: ▼ Checkpoint #5
| Task Series ① | ⓐ | Pln
Act
|  | ⓑ | Pln
Act
|  | ⓒ | Pln
Act
|  | ⓓ | Pln
Act
| Task Series ② | ⓐ | Pln
Act
|  | ⓑ | Pln
Act
|  | ⓒ | Pln
Act
|  | ⓓ | Pln
Act
|  | ⓔ | Pln
Act
|  | ⓕ | Pln
Act
| Task Series ③ | ⓐ | Pln
Act
|  | ⓑ | Pln
Act
|  | ⓒ | Pln
Act
|  | ⓓ | Pln
Act
| Project Report | Document prep | Pln | bar: Week 19 20 Mo to Week 21 5 We
Act
|  | Management reviews | Pln | Week 19 23 Th: 1; Week 20 30 Th: 2; Week 21 4 Tu: 3
Act
|  | Release | Pln | bar: Week 21 6 Th
Act
Project #2 Title: Goal: | Milestones |  |  | Week 1 16 Tu: ▼ Project kickoff; Week 4 8 Th: ▼ Checkpoint #1; Week 8 7 Th: ▼ Checkpoint #2; Week 12 4 Th: ▼ Checkpoint #3; Week 16 2 Th: ▼ Checkpoint #4; Week 20 30 Th: ▼ Checkpoint #5
| Task Series ① | ⓐ | Pln
Act
|  | ⓑ | Pln
Act
|  | ⓒ | Pln
Act
|  | ⓓ | Pln
Act
| Task Series ② | ⓐ | Pln
Act
|  | ⓑ | Pln
Act
|  | ⓒ | Pln
Act
|  | ⓓ | Pln
Act
|  | ⓔ | Pln
Act
|  | ⓕ | Pln
Act
| Task Series ③ | ⓐ | Pln
Act
|  | ⓑ | Pln
Act
|  | ⓒ | Pln
Act
|  | ⓓ | Pln
Act
| Project Report | Document prep | Pln | bar: Week 19 20 Mo to Week 21 5 We
Act
|  | Management reviews | Pln | Week 19 23 Th: 1; Week 20 30 Th: 2; Week 21 4 Tu: 3
Act
|  | Release | Pln | bar: Week 21 6 Th
Act
Project #3 Title: Goal: | Milestones |  |  | Week 1 16 Tu: ▼ Project kickoff; Week 4 8 Th: ▼ Checkpoint #1; Week 8 7 Th: ▼ Checkpoint #2; Week 12 4 Th: ▼ Checkpoint #3; Week 16 2 Th: ▼ Checkpoint #4; Week 20 30 Th: ▼ Checkpoint #5
| Task Series ① | ⓐ | Pln
Act
|  | ⓑ | Pln
Act
|  | ⓒ | Pln
Act
|  | ⓓ | Pln
Act
| Task Series ② | ⓐ | Pln
Act
|  | ⓑ | Pln
Act
|  | ⓒ | Pln
Act
|  | ⓓ | Pln
Act
|  | ⓔ | Pln
Act
|  | ⓕ | Pln
Act
| Task Series ③ | ⓐ | Pln
Act
|  | ⓑ | Pln
Act
|  | ⓒ | Pln
Act
|  | ⓓ | Pln
Act
| Project Report | Document prep | Pln | bar: Week 19 20 Mo to Week 21 5 We
Act
|  | Management reviews | Pln | Week 19 23 Th: 1; Week 20 30 Th: 2; Week 21 4 Tu: 3
Act
|  | Release | Pln | bar: Week 21 6 Th
Act